## Korea
Marketing budget
No | Type | Mareting Activity Name | Priority | Dependency | Owner | Budget | Global Target due | START DATE | END DATE (Target due) | DURATION (WORK DAYS) | PERCENT COMPLETE | 2019 Jan |  |  |  | 2019 Feb |  |  |  | 2019 Mar |  |  |  | 2019 Apr |  |  |  | 2019 May |  |  |  | 2019 Jun |  |  |  | 2019 Jul |  |  |  | 2019 Aug |  |  |  | 2019 Sep |  |  |  | 2019 Oct |  |  |  | 2019 Nov |  |  |  | 2019 Dec |  |  |  | 2020 Jan |  |  |  | 2020 Feb |  |  |  | 2020 Mar |  |  |  |  | 2020 Apr |  |  |  | 2020 May |  |  |  | 2020 Jun |  |  |  | 2020 Jul |  |  |  | 2020 Aug |  |  |  | 2020 Sep |  |  |  | 2020 Oct |  |  |  | 2020 Nov |  |  |  | 2020 Dec
[12 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1 | Event | 9 |  |  |  | 29800 |  | - | - | -
1.1 | Event | Event 1 |  | division OOO | AAA | 3000 |  | 2019-10-24 | 2019-10-24 | 1 | 100% | bar: 2019 Oct W4
1.2 | Event | Event 2 |  | division O | BBB | 1900 |  | 2019-10-25 | 2020-01-06 | 52 | 100% | bar: 2019 Oct W4
1.3 | Event | Event 3 |  | division OO | CCC | 2500 |  | 2020-01-01 | 2020-01-06 | 4 | 100% | bar: 2019 Nov W3 to 2019 Dec W2; 2020 Jan W1
1.4 | Event | Event 4 |  | division O | DDD | 1400 |  | 2020-01-01 | 2020-01-06 | 4 | 100% | bar: 2019 Nov W3 to 2019 Dec W2; 2020 Jan W1
1.5 | Event | Event 5 |  | division OOO | EEE | 2200 |  | 2020-01-01 | 2020-01-06 | 4 | 100% | bar: 2019 Nov W3 to 2019 Dec W2; 2020 Jan W1
1.6 | Event | Event 6 |  | division OO | FFF | 2800 |  | 2020-01-01 | 2020-01-06 | 4 | 100% | bar: 2019 Nov W3 to 2019 Dec W2; 2020 Jan W1
1.7 | Event | Event 7 |  | division O | GGG | 4500 | 2019-11-15 | 2020-01-01 | 2020-01-06 | 4 | 100% | bar: 2019 Nov W3 to 2019 Dec W2; 2020 Jan W1
1.8 | Event | Event 8 |  | division OOO | HHH | 6200 | 2019-12-15 | 2020-01-01 | 2020-01-06 | 4 | 100% | bar: 2019 Nov W3 to 2019 Dec W2; 2020 Jan W1
1.9 | Event | Event 9 |  | division OO | III | 5300 | 2019-12-25 | 2020-01-01 | 2020-01-06 | 4 | 100% | bar: 2019 Nov W3 to 2019 Dec W2; 2020 Jan W1
2 | Promotion | 6 |  |  |  | 12450 |  | - | - | - | bar: 2020 Jan W1
2.1 | Promotion | Promotion 1 |  | division OOO | AAA | 1200 | 2019-11-15 | 2019-11-15 | 2019-11-15 | 1 | 100% | bar: 2019 Nov W2 to 2019 Nov W3
2.2 | Promotion | Promotion 2 |  | division O | BBB | 800 | 2019-11-18 | 2019-11-18 | 2019-11-18 | 1 | 100% | bar: 2019 Nov W2 to 2019 Nov W3
2.3 | Promotion | Promotion 3 |  | division OO | CCC | 1600 | 2020-01-30 | 2020-02-19 | 2020-02-19 |  | 100% | bar: 2019 Nov W3 to 2019 Dec W1
2.4 | Promotion | Promotion 4 |  | division O | DDD | 2900 | 2020-01-31 | 2020-02-19 | 2020-01-17 |  | 100% | bar: 2019 Nov W3 to 2019 Dec W1; 2020 Feb W3
2.5 | Promotion | Promotion 5 |  | division OOO | EEE | 3100 | 2020-01-31 | 2020-02-19 | 2020-01-17 |  | 100% | bar: 2019 Nov W3 to 2019 Dec W1; 2020 Feb W3
2.6 | Promotion | Promotion 6 |  | division O | FFF | 2850 | 2020-01-31 | 2020-01-30 | 2020-01-21 |  | 100% | bar: 2019 Nov W3 to 2019 Dec W1; 2020 Feb W1
3 | Advertisement | 5 |  |  |  | 4910 | - | - | - | -
3.1 | Advertisement | Advertisement 1 |  | division OOO | AAA | 480 | 2019-10-16 | 2019-11-25 | 2020-01-31 | 50 | 100% | bar: 2019 Nov W3 to 2019 Dec W1; 2020 Jan W4
3.2 | Advertisement | Advertisement 2 |  | division O | BBB | 760 | 2019-11-01 | 2019-11-23 | 2019-12-03 | 7 | 100% | bar: 2019 Nov W3 to 2019 Dec W2
3.3 | Advertisement | Advertisement 3 |  | division OO | CCC | 1020 | 2019-11-30 |  | 2019-11-15 |  | 100% | bar: 2019 Nov W3 to 2019 Dec W1; 2019 Dec W3
3.4 | Advertisement | Advertisement 4 |  | division O | DDD | 450 | 2019-12-06 |  | 2019-12-06 |  | 100% | bar: 2019 Nov W3 to 2019 Dec W2
3.5 | Advertisement | Advertisement 5 |  | division OOO | EEE | 2200 | 2019-12-14 |  | 2019-12-14 |  | 100% | bar: 2019 Nov W3 to 2019 Dec W1; 2019 Dec W3
4 | Demo unit | 6 |  |  |  | 18300 | - | - | - | -
4.1 | Demo unit | Demo 1 |  | division OOO | AAA | 4500 | 2019-12-14 | 2019-12-02 | 2019-12-13 | 10 | 100% | bar: 2019 Dec W1 to 2019 Dec W2
4.2 | Demo unit | Demo 2 |  | division O | BBB | 2200 | 2019-12-20 |  | 2019-12-20 |  | 100% | bar: 2019 Dec W1 to 2019 Dec W2
4.3 | Demo unit | Demo 3 |  | division OO | CCC | 2800 | 2020-01-15 |  | 2020-01-15 |  | 100% | bar: 2019 Dec W1 to 2019 Dec W2
4.4 | Demo unit | Demo 4 |  | division O | DDD | 3000 |  | 2020-04-24 | 2020-05-22 |  | 80% | bar: 2020 May W1
4.5 | Demo unit | Demo 5 |  | division OOO | EEE | 2600 |  |  | 2020-05-30 |  | 0%
4.6 | Demo unit | Demo 6 |  | division OO | FFF | 3200 |  |  | 2020-05-30 |  | 0%
| Total | 26 |  |  |  | 65460
| Sum of Budget | Column Labels
| Row Labels | division OOO | division O | division OO | Grand Total | division OOO | division O | division OO | Grand Total
| Advertisement | 2680 | 1210 | 1020 | 4910 | 8.065% | 19.8% | 10.87% | 11.34%
| Demo unit | 7100 | 5200 | 6000 | 18300 | 4.412% | 3.792% | 9.091% | 5.719%
| Event | 11400 | 7800 | 10600 | 29800 | 11.76% | 4.698% | 6.426% | 7.932%
| Promotion | 4300 | 6550 | 1600 | 12450 | 16.22% | 4.8% | 14.29% | 9.692%
| Grand Total | 25480 | 20760 | 19220 | 65460 | 9.922% | 5.274% | 8.099% | 7.877%
| 2018 | division OOO | division O | division OO | Grand Total
| Advertisement | 2480 | 1010 | 920 | 4410
| Demo unit | 6800 | 5010 | 5500 | 17310
| Event | 10200 | 7450 | 9960 | 27610
| Promotion | 3700 | 6250 | 1400 | 11350
| Grand Total | 23180 | 19720 | 17780 | 60680